## Slide 1: CASA 1000 SANGTUDA-NOWSHERA HVDC PACKAGE
PRE-BID MEETING AT DUBAI
05-12-2016

## Slide 2: SANGTUDA-NOWSHERA HVDC PACKAGE
Questions Broadly categorized under Three(3) Heads;
- Issues need discussions for Clarification /Conclusion
- Clarifications/Additional Information to be issued in writing
- Missing Information/Typo Errors to be issued in writing
Based on the discussions on the Pre-Bid Meeting, the following documents shall be issued to all the Bidders
-Records notes of Discussions,
- Clarifications and additional/missing information
- Amendments wherever required

## Slide 3: SANGTUDA-NOWSHERA HVDC PACKAGE
Two Stage Bidding Process as per the Standard Bidding Document of the World Bank.
- First Stage Bid -Technical/Commercial Proposals are Unpriced
Based on review and discussions, “ Changes Required Pursuant
to First Stage Evaluation” shall be issued.
- Second Stage Bid- Price Bid

## Slide 4
COMMERCIAL

## Slide 5: SANGTUDA-NOWSHERA HVDC PACKAGE PART-1 of the Bid Document
Source of Funds;
Loans from;
- International Development Association
- EBRD
- Department of International Development UK,
- USAID
- And Other Banks
What is the Quantum of Funds and how they are allocated to the Borrowers?

## Slide 6: CASA-1000, HVDC PACKAGE . PART-1
SCOPE OF WORK
PAKISTAN
- 1300 MW Converter Station at Nowshera
- Electrode Station
- Repeater Station within Pakistan, If Required
- One 500 kV Diameter with provision for interconnection to 500 kV
switchyard of NTDC. All protection and control ( including cabling)
- Maintenance Support Services for Converter Station with repeater
Station and electrode station.

## Slide 7: CASA-1000, HVDC PACKAGE . PART-1
SCOPE OF WORK Contd.
Tajikistan
- Converter Station at Sangtuda
- Electrode Station
- Repeater Station within Tajikistan, If Required ,
- One 500 kV ICT Bay at New Sangtuda 500 kV S/S
- 4 X 167 MVA, 500 /220 kV, ICT
- One 500 kV line bay at New Sangtuda
- 220 kV Switch yard at New Sangtuda S/S with one Transformer bay and line bay
- One 220 kV line bay at existing 220 kV S/S
- Maintenance Support Services for Converter Station with repeater
Station and electrode station.

## Slide 8: CASA-1000, HVDC PACKAGE . PART-1
SCOPE OF WORK Contd.
Afghanistan
- Repeater Stations within Afghanistan
- Maintenance Support Services for Repeater Stations.
HVDC TRANSMISSION LINE INCLUDING OPGW INTERCONNECTING SANGTUDA AND NOWSHERA TERMINAL STATIONS AND ELECTRODE LINES AT SANGTUDA AND NOWSHERA END ARE BEING PROCURED SEPARATELY

## Slide 9: CASA-1000, HVDC PACKAGE . PART-1 Maintenance Support Services(MSS)
Scope of work-MSS initially for 2 Years can be extended on mutually agreed terms and conditions at Sangtuda and Nowshera.
Sl. NO | Area of Expertise | No of Experts Per Location
1 | Converter Transformer & Accessories | 1
2 | Thyristor valves , associated subsystems including valve cooling | 1
3 | HVDC Controls & Protection System (HW/SW) | 2
4 | AC/DC Switch yard including filters and Electrical & Mechanical auxiliaries . | 1
 | TOTAL | 5

## Slide 10: CASA-1000, HVDC PACKAGE . GENERAL
Status of Acquisition of Site location at Nowshera and Sangtuda
Latest project map to show project locations
Visit of site location by Bidder(s) with the permission of Employers
Security of Personnel & operations be managed at site during bidding stage ( e.g. site and soil survey) and during execution
Is there any secured residential compound for contractors personnel?
Supporting letter for obtaining Visa
A copy of CASA REA EMP for Tajikistan & Pakistan
Who owns HVDC converter Stations and HVDC line once completed?
Who will operate the HVDC Link ?
Road surveys for heavy cargo transportation or any constraint ?

## Slide 11: CASA-1000, HVDC PACKAGE . PART-1
ELECTRONIC BID SUBMISSION;
- Refer BDS ITB 21.1- It is not Permitted.
However , the Bidder should submit an Electronic copy for
internal use of Employers. Shall not be considered for Evaluation
BID SECURITY/ Other Guarantees
In case of a Bid from Joint Venture, the Bid Security in the name of the JV. Not in the name of Lead Partner or other partners
Construction of Contract;
What will be contractual arrangement at Execution stage? Will it be one contract signed with IGC? If two separate contracts , will there be an umbrella agreements( as T&C s and Provisions on one side can impact the other side)

## Slide 12: CASA-1000, HVDC PACKAGE . PART-1
Construction of Contract;
- Total Six (6) Contract
- Separate contracts( Total-4 Nos) Country wise (2 no) for the Project;
Tajikistan -2 ( Nos ) and Pakistan -2 ( Nos)
First Contract- For supply of plant & equipment from abroad
Second Contract- Rest of the supplies and services within each of
the country.
Cross Fall breach clause amongst 4 contracts
- Separate contracts ( Total- 2 Nos) for Maintenance Support Services
Tajakistan- 1 No and Pakistan -1 No
Cross Fall breach clause amongst these 2 contracts
No cross fall clause on Project Contracts and Maintenance Support services contract

## Slide 13: CASA-1000, HVDC PACKAGE . PART-1
EXCLUSIVENESS or UNIQUENESS of Joint Deed of Undertaking OR can join more than one Bidder
What is the reasoning of Joint of Under Taking ( Jointly & Several Responsibility)
The Qualification Criteria as defined in Section III (2.3.1) and average annual turnover requirements (2.3.2) is applicable for legal entities wishing to enter in to a consortium for tax reasons but belonging to the same group
Being the First HVDC project in both countries similar job shall be considered as only substation job for the assignee(s)

## Slide 14: CASA-1000, HVDC PACKAGE . PART-3
The Liquidated damages for functional gurantees should not exceed X % of contract value
The Defect Liability Period should not exceed 2 Years from taking over or 3 years from the date of Delivery which ever earlier. The extended Defect Liability Period should not exceed three years from taking over
Force Majeure shall not include “ Govt actions/restrictions, threats from any organizations,any fatal incident at site and communicable diseases”
Two contracts for Two Terminal stations in Tajikistan and Pakistan. Pl confirm that it will be governed by individual country law

## Slide 15: CASA-1000, HVDC PACKAGE . PART-3
Clarify the responsibilities of the Contractor and of the Employer on the payment of Duties, sales tax etc
What is the applicable Tax on Design, Engineering , Civil & Erection portion of the contract and Who shall bear it ?
What shall be the payment mechanism as it involves two Utilities and two countries ?
- Whether the Contractor raise Sangtuda and Nowshera related
invoices to Tajikistan and Pakistan Utility respectively?
- How shall LC opened whether common for the entire project or
Separate LC for each Country contract?
- Whether both the contracts shall be treated independently with
independent administrative structure or common structure
for better co-ordination

## Slide 16: CASA-1000, HVDC PACKAGE . PART-3
Project Completion Period;
Project completion time is short given the complexity and location of
project. Completion Period be extended to 48 Months.
Change order shall be restricted to X% of contract price. No negative change order
Termination shall be in full and no termination shall be on a part of the facilities.

## Slide 17: CASA-1000, HVDC PACKAGE . PART-3
Time Limit for Drawing/Document Approval by the Employer
Sole & Exclusive remedy
The remedies provided under the contract shall be the sole and
exclusive remedy available to the Employer to the exclusion of any
other remedies available under law or otherwise
Please specify clearly what responsibilities the contractor is expected to take regarding security arrangements in the project
Please provide a detailed security plan for the project, including the specific sites
Request to extent First Stage Bid submission to End April’17

## Slide 18
TECHNICAL

## Slide 19: CASA-1000, HVDC PACKAGE . PART-2
Geological/Weather information
-Detail survey & soil investigation report ( Geo-technical & resistivity) of the converter locations at Sangtuda and Nowshera
- Cooling Water Temperature at Sangtuda & Nowshera
- Solar radiation strength in W/sq. cm
- Seismic horizontal acceleration of Sangtuda , pl clarify what does
mean by “Third category ,7” in terms of horizontal acceleration “g”
- Environmental data of Afghanistan be provided
Repeater stations be deleted from the present scope.
Obligation of Contractor in context of Environmental & Social Mitigation measures shall be clearly spelled out.

## Slide 20: CASA-1000, HVDC PACKAGE . PART-2
Auxiliary Supply sources converter stations at Sangtuda & Nowshera
Power Supply arrangement for charging the HVDC line during 7 months non operational period
Monopolar Power flow of 5% is low , be enhanced to 10%
Power System Network Data of Tajikistan and Pakistan existing & future.
Details like layout & SLD of Existing 500 kV Nowshera Substation & 500 & 220 kV Sangtuda Substation along with distances. Control & Protection details of interconnecting facilities.
Details of HVDC line , Optical fibre and Earth Electrode line including length.
Can the maintenance be performed by Employer trained personnel?

## Slide 21: CASA-1000, HVDC PACKAGE . PART-2
Is 5 Months ( From 1st May to 30th September- Termed as Block Year) shall be considered for analysis and also meeting availability & reliability guarantee period ?
Details Employers Emergency Control Devices (ECD) be provided. Contractors responsibility only lies providing necessary signals to ECD
Kindly clarify no of Remote Control Centre/LDC etc intentioned to be communicated for control and monitoring purpose
Kindly clarify the type of Building RCC/Pre-fabricated for Repeaters
Minor clarifications/ additional informations have been received , the same shall be clarified/sent in writing to all the Bidders.

## Slide 22: CASA-1000, HVDC PACKAGE .
Overall Time Lines;
Submission of Stage 1 Bid - 06th Feb 2017
Completion of Stage 1 Techno-Commercial Discussions- 3/4 Months
Invitation of Stage 2 Bid – 1 Month
Evaluation and Award - 2/3 Months
Completion Period - 42 Months

## Slide 23
THANK YOU